NavAlert

Development Gantt & Component Timeline

Capstone Project - BSIT, Polytechnic University of the Philippines   ·   Version 1.0.0   ·   ph.edu.pup.navalert

## Project overview

Development schedule for NavAlert v1.0.0, delivered as a BSIT team capstone over the June to August semester. Every screen, service, view-model, native class, asset, generator, and test suite appears on the timeline, sequenced the way the team worked: design before build, services before the screens that consume them, and features before the tests that cover them. Parallel tracks let the app core, routing, safety, and interface progress at the same time; weekends are left clear on every chart.

Work ran in weekly cycles around class schedules, anchored by regular adviser consultations, a midterm demo, and a focused revision pass after each round of feedback before the final defense build.

## Workstreams

App core & data — architecture, encrypted storage, view-models, app shell

Routing & maps — GTFS pipeline, Dijkstra multimodal router, offline tiles

Guide & alarm — step-by-step commute guide, adaptive destination alarm

Safety — SOS, verified SMS delivery, fake incoming call

UI / UX — screens, design system, layout parity

Native Android — SMS bridge, media-session volume, home-screen widget

QA — unit, widget, and full trip-flow simulation suites

Design & assets — branding, sounds, tutorial artwork, generators

## Key dates

Concept Jun 1   ·   proposal defense Jun 5   ·   foundation ready Jul 16   ·   adviser midterm demo Jul 24   ·   router online Jul 30   ·   feature-complete Aug 6   ·   v1.0.0 defense build and capstone defense Aug 8.

# 1.  Master feature Gantt  (3 pages)

## 1.  Master feature Gantt  (continued - Part 2 of 3)

## 1.  Master feature Gantt  (continued - Part 3 of 3)

# 2.  Services layer  (lib/services/) - all 20 files

# 3.  UI / Views  (lib/views/) - all 17 screens and widgets

# 4.  ViewModels & Core  (viewmodels / core / models)

# 5.  Native Android  (kotlin + resources)

# 6.  Assets & tooling  (assets/ , tool/)

# 7.  Test suite  (test/ , integration_test/) - 21 suites, 280 tests

# 8.  Milestones

| Milestone | Date | What it marks |
| --- | --- | --- |
| Title / proposal defense | 2026-06-05 | Topic and scope approved by the panel; problem and objectives set |
| Concept locked | 2026-07-02 | Alarm math, design rationale, legal docs, and tutorial assets finalized |
| Ethics & data-privacy sign-off | 2026-07-15 | Encrypted storage and consent flow cleared for user testing |
| Foundation ready | 2026-07-16 | Flutter + MVVM scaffold, theme, and encrypted storage in place |
| Adviser midterm demo | 2026-07-24 | Working planning flow shown to the adviser; feedback logged |
| Router online | 2026-07-30 | Dijkstra multimodal routing over bundled GTFS working end to end |
| Feature-complete | 2026-08-06 | All primary and secondary features present, opt-in alarm wired |
| Pre-defense dry run | 2026-08-07 | Full walkthrough on hardware; last blocking bugs triaged |
| v1.0.0 defense build / Capstone defense | 2026-08-08 | Verified-SMS, offline maps, 280 tests passing — presented |

# 9.  Appendix - every file, its window, and its track

Every source file, asset, generator, and test suite in the build, grouped by the workstream that owned it, with the date work started and the working window on the schedule.

Dart - core, models, view-models

| File | Started | Working window | Track |
| --- | --- | --- | --- |
| lib/main.dart | Jul 01 | 3d | App core |
| lib/core/theme.dart | Jul 04 | 5d | App core |
| lib/core/map_support.dart | Jul 28 | 3d | Routing |
| lib/models/models.dart | Jul 07 | 4d | App core |
| lib/models/guide_leg.dart | Jul 23 | 3d | Guide & alarm |
| lib/viewmodels/app_viewmodel.dart | Jul 03 | 3d | App core |
| lib/viewmodels/home_viewmodel.dart | Jul 08 | 6d | App core |
| lib/viewmodels/trip_viewmodel.dart | Jul 10 | 8d | Guide & alarm |
| lib/viewmodels/emergency_viewmodel.dart | Jul 13 | 4d | Safety |
| lib/viewmodels/history_viewmodel.dart | Jul 14 | 3d | App core |

Dart - services

| File | Started | Working window | Track |
| --- | --- | --- | --- |
| lib/services/database_service.dart | Jul 10 -> Aug 03 | 6d + 2d | Data |
| lib/services/geocoding_service.dart | Jul 09 | 5d | Routing |
| lib/services/route_engine.dart | Jul 12 | 6d | Routing |
| lib/services/route_path_service.dart | Jul 21 | 5d | Routing |
| lib/services/sound_service.dart | Jul 14 | 6d | Safety |
| lib/services/sos_service.dart | Jul 17 | 6d | Safety |
| lib/services/adaptive_alarm_engine.dart | Jul 18 | 10d | Guide & alarm |
| lib/services/trip_notification_service.dart | Jul 22 | 5d | Guide & alarm |
| lib/services/hardware_buttons.dart | Jul 25 | 4d | Safety |
| lib/services/gtfs_service.dart | Jul 18 | 5d | Routing |
| lib/services/transit_graph.dart | Jul 22 | 4d | Routing |
| lib/services/transit_router.dart | Jul 24 | 6d | Routing |
| lib/services/routing_isolate.dart | Jul 29 | 3d | Routing |
| lib/services/guide_progress.dart | Jul 25 | 4d | Guide & alarm |
| lib/services/fake_call_screen_service.dart | Jul 21 | 5d | Safety |
| lib/services/home_widget_service.dart | Aug 01 | 4d | Native bridge |
| lib/services/tile_cache_store.dart | Aug 04 | 3d | Data |

Dart - views

| File | Started | Working window | Track |
| --- | --- | --- | --- |
| lib/views/shell.dart | Jul 05 | 4d | UI / UX |
| lib/views/launch_view.dart | Jul 07 | 2d | UI / UX |
| lib/views/onboarding_flow.dart | Jul 09 | 6d | UI / UX |
| lib/views/home_view.dart | Jul 11 | 6d | UI / UX |
| lib/views/search_view.dart | Jul 16 | 4d | UI / UX |
| lib/views/route_view.dart | Jul 18 | 6d | UI / UX |
| lib/views/pin_on_map_view.dart | Jul 19 | 4d | UI / UX |
| lib/views/active_trip_view.dart | Jul 22 | 6d | UI / UX |
| lib/views/commute_guide_sheet.dart | Jul 25 | 5d | UI / UX |
| lib/views/trip_map.dart | Aug 01 | 3d | UI / UX |
| lib/views/commute_sheet_layout.dart | Aug 03 | 3d | UI / UX |
| lib/views/emergency_view.dart | Jul 14 | 5d | Safety |
| lib/views/fake_call_view.dart | Jul 18 | 4d | Safety |
| lib/views/favorites_view.dart | Jul 13 | 3d | UI / UX |
| lib/views/history_view.dart | Jul 15 | 3d | UI / UX |
| lib/views/add_favorite_view.dart | Jul 16 | 3d | UI / UX |
| lib/views/settings_view.dart | Jul 17 | 4d | UI / UX |

Native Android

| File | Started | Working window | Track |
| --- | --- | --- | --- |
| MainActivity.kt (SMS bridge) | Jul 14 -> Aug 04 | 5d + 3d | Native |
| MediaButtonService.kt | Jul 25 | 4d | Native |
| NavAlertWidgetProvider.kt | Aug 01 | 4d | Native |
| res/layout/navalert_widget.xml | Aug 01 | 2d | Native |
| res/drawable/widget_bg.xml, widget_sos_bg.xml | Aug 02 | 2d | Native |
| res/xml/navalert_widget_info.xml | Aug 02 | 1d | Native |
| res/mipmap-anydpi-v26/ic_launcher.xml | Aug 06 | 2d | Native |
| res/drawable/launch_background.xml + styles.xml | Jul 04 | 2d | Native |
| res/values/colors.xml + values-night/styles.xml | Aug 06 | 2d | Native |
| AndroidManifest.xml | Jul 02 | 3d | Native |

Assets & tooling

| File | Started | Working window | Track |
| --- | --- | --- | --- |
| assets/images/tutorial/* + reference/* | Jun 25 | 7d | Design & assets |
| assets/images/branding/main_bg.png | Jun 25 | 7d | Design & assets |
| assets/icons/ALARMA APP ICON.png | Aug 06 | 2d | Design & assets |
| assets/sounds/*.wav (7 alarm sounds) | Jul 14 | 3d | Design & assets |
| assets/sounds/fake_call_mom.wav, fake_call_dad.wav | Aug 01 | 2d | Design & assets |
| assets/gtfs/routes.json.gz + NOTICE.md | Jul 17 | 2d | Routing |
| tool/gen_sounds.dart | Jul 13 | 2d | Tooling |
| tool/gen_gtfs.py | Jul 15 | 3d | Tooling |
| tool/gen_launcher_icons.py | Aug 06 | 2d | Tooling |

Test suites

| File | Started | Working window | Track |
| --- | --- | --- | --- |
| test/models_test.dart | Jul 20 | 2d | QA |
| test/route_engine_test.dart | Jul 22 | 2d | QA |
| test/assets_test.dart | Jul 24 | 1d | QA |
| test/adaptive_alarm_engine_test.dart | Jul 26 | 2d | QA |
| test/gtfs_service_test.dart | Jul 24 | 2d | QA |
| test/transit_graph_real_test.dart | Jul 28 | 2d | QA |
| test/transit_router_test.dart | Jul 30 | 2d | QA |
| test/guide_progress_test.dart | Jul 31 | 2d | QA |
| test/trip_flow_test.dart | Aug 01 | 3d | QA |
| integration_test/full_app_sweep_test.dart | Aug 04 | 3d | QA |
| test/trip_camera_tracker_test.dart | Aug 05 | 2d | QA |
| test/sos_failure_reporting_test.dart | Jul 22 | 3d | QA |
| test/contact_form_test.dart | Aug 01 | 2d | QA |
| test/schema_guard_test.dart | Aug 04 | 2d | QA |
| test/home_fab_layout_test.dart | Jul 31 | 2d | QA |
| test/home_live_location_test.dart | Aug 04 | 2d | QA |
| test/commute_guide_overlay_test.dart | Aug 05 | 2d | QA |
| test/marker_glide_test.dart | Aug 05 | 2d | QA |
| test/commute_sheet_layout_test.dart | Aug 06 | 2d | QA |
| test/tile_cache_store_test.dart | Aug 05 | 2d | QA |
| test/trip_notification_text_test.dart | Aug 07 | 1d | QA |

NavAlert v1.0.0 development schedule — BSIT capstone, Polytechnic University of the Philippines, culminating in the defense build on 2026-08-08.